## Dashboard
GRAPHIC DESIGN STUDIO MANAGEMENT DASHBOARD
KPI Metric | Value | Status Summary
Total Portfolio Budget | 0 | Briefing | 10
Total Amount Collected | 0 | In Progress | 10
Total Outstanding Balance | 0 | Review | 10
Total Projects Tracked | 50 | Approved | 10
|  | On Hold | 10

## Client Database
Client ID | Client Name | Company | Contact Email | Status | Total Projects | Lifetime Revenue
DS-CLN-001 | Client Name 1 | Design Labs LLC 1 | contact@enterprise1.com | Active | 5 | 22500
DS-CLN-002 | Client Name 2 | Creative Enterprise 2 | contact@enterprise2.com | Active | 5 | 18000
DS-CLN-003 | Client Name 3 | Design Labs LLC 3 | contact@enterprise3.com | Active | 5 | 18500
DS-CLN-004 | Client Name 4 | Creative Enterprise 4 | contact@enterprise4.com | Active | 5 | 19000
DS-CLN-005 | Client Name 5 | Design Labs LLC 5 | contact@enterprise5.com | Active | 5 | 19500
DS-CLN-006 | Client Name 6 | Creative Enterprise 6 | contact@enterprise6.com | Active | 5 | 20000
DS-CLN-007 | Client Name 7 | Design Labs LLC 7 | contact@enterprise7.com | Inactive | 5 | 20500
DS-CLN-008 | Client Name 8 | Creative Enterprise 8 | contact@enterprise8.com | Active | 5 | 21000
DS-CLN-009 | Client Name 9 | Design Labs LLC 9 | contact@enterprise9.com | Active | 5 | 21500
DS-CLN-010 | Client Name 10 | Creative Enterprise 10 | contact@enterprise10.com | Active | 5 | 22000
DS-CLN-011 | Client Name 11 | Design Labs LLC 11 | contact@enterprise11.com | Active | 0 | 0
DS-CLN-012 | Client Name 12 | Creative Enterprise 12 | contact@enterprise12.com | Active | 0 | 0
DS-CLN-013 | Client Name 13 | Design Labs LLC 13 | contact@enterprise13.com | Active | 0 | 0
DS-CLN-014 | Client Name 14 | Creative Enterprise 14 | contact@enterprise14.com | Inactive | 0 | 0
DS-CLN-015 | Client Name 15 | Design Labs LLC 15 | contact@enterprise15.com | Active | 0 | 0
DS-CLN-016 | Client Name 16 | Creative Enterprise 16 | contact@enterprise16.com | Active | 0 | 0
DS-CLN-017 | Client Name 17 | Design Labs LLC 17 | contact@enterprise17.com | Active | 0 | 0
DS-CLN-018 | Client Name 18 | Creative Enterprise 18 | contact@enterprise18.com | Active | 0 | 0
DS-CLN-019 | Client Name 19 | Design Labs LLC 19 | contact@enterprise19.com | Active | 0 | 0
DS-CLN-020 | Client Name 20 | Creative Enterprise 20 | contact@enterprise20.com | Active | 0 | 0
DS-CLN-021 | Client Name 21 | Design Labs LLC 21 | contact@enterprise21.com | Inactive | 0 | 0
DS-CLN-022 | Client Name 22 | Creative Enterprise 22 | contact@enterprise22.com | Active | 0 | 0
DS-CLN-023 | Client Name 23 | Design Labs LLC 23 | contact@enterprise23.com | Active | 0 | 0
DS-CLN-024 | Client Name 24 | Creative Enterprise 24 | contact@enterprise24.com | Active | 0 | 0
DS-CLN-025 | Client Name 25 | Design Labs LLC 25 | contact@enterprise25.com | Active | 0 | 0
DS-CLN-026 | Client Name 26 | Creative Enterprise 26 | contact@enterprise26.com | Active | 0 | 0
DS-CLN-027 | Client Name 27 | Design Labs LLC 27 | contact@enterprise27.com | Active | 0 | 0
DS-CLN-028 | Client Name 28 | Creative Enterprise 28 | contact@enterprise28.com | Inactive | 0 | 0
DS-CLN-029 | Client Name 29 | Design Labs LLC 29 | contact@enterprise29.com | Active | 0 | 0
DS-CLN-030 | Client Name 30 | Creative Enterprise 30 | contact@enterprise30.com | Active | 0 | 0
DS-CLN-031 | Client Name 31 | Design Labs LLC 31 | contact@enterprise31.com | Active | 0 | 0
DS-CLN-032 | Client Name 32 | Creative Enterprise 32 | contact@enterprise32.com | Active | 0 | 0
DS-CLN-033 | Client Name 33 | Design Labs LLC 33 | contact@enterprise33.com | Active | 0 | 0
DS-CLN-034 | Client Name 34 | Creative Enterprise 34 | contact@enterprise34.com | Active | 0 | 0
DS-CLN-035 | Client Name 35 | Design Labs LLC 35 | contact@enterprise35.com | Inactive | 0 | 0
DS-CLN-036 | Client Name 36 | Creative Enterprise 36 | contact@enterprise36.com | Active | 0 | 0
DS-CLN-037 | Client Name 37 | Design Labs LLC 37 | contact@enterprise37.com | Active | 0 | 0
DS-CLN-038 | Client Name 38 | Creative Enterprise 38 | contact@enterprise38.com | Active | 0 | 0
DS-CLN-039 | Client Name 39 | Design Labs LLC 39 | contact@enterprise39.com | Active | 0 | 0
DS-CLN-040 | Client Name 40 | Creative Enterprise 40 | contact@enterprise40.com | Active | 0 | 0
DS-CLN-041 | Client Name 41 | Design Labs LLC 41 | contact@enterprise41.com | Active | 0 | 0
DS-CLN-042 | Client Name 42 | Creative Enterprise 42 | contact@enterprise42.com | Inactive | 0 | 0
DS-CLN-043 | Client Name 43 | Design Labs LLC 43 | contact@enterprise43.com | Active | 0 | 0
DS-CLN-044 | Client Name 44 | Creative Enterprise 44 | contact@enterprise44.com | Active | 0 | 0
DS-CLN-045 | Client Name 45 | Design Labs LLC 45 | contact@enterprise45.com | Active | 0 | 0
DS-CLN-046 | Client Name 46 | Creative Enterprise 46 | contact@enterprise46.com | Active | 0 | 0
DS-CLN-047 | Client Name 47 | Design Labs LLC 47 | contact@enterprise47.com | Active | 0 | 0
DS-CLN-048 | Client Name 48 | Creative Enterprise 48 | contact@enterprise48.com | Active | 0 | 0
DS-CLN-049 | Client Name 49 | Design Labs LLC 49 | contact@enterprise49.com | Inactive | 0 | 0
DS-CLN-050 | Client Name 50 | Creative Enterprise 50 | contact@enterprise50.com | Active | 0 | 0

## Project Pipeline
Project ID | Project Name | Client ID | Project Type | Assigned Designer | Start Date | Due Date | Status | Progress (%) | Overdue Status
DS-PRJ-001 | Campaign Project 1 | DS-CLN-002 | Web Design | Muhammad Jawad | 2026-05-02 | 2026-05-16 | In Progress | 50% | OVERDUE
DS-PRJ-002 | Campaign Project 2 | DS-CLN-003 | UI/UX | Sarah Khan | 2026-05-03 | 2026-05-17 | Review | 50% | OVERDUE
DS-PRJ-003 | Campaign Project 3 | DS-CLN-004 | Social Media | Zain Ahmed | 2026-05-04 | 2026-05-18 | Approved | 100% | Completed
DS-PRJ-004 | Campaign Project 4 | DS-CLN-005 | Packaging | Amna Javed | 2026-05-05 | 2026-05-19 | On Hold | 50% | OVERDUE
DS-PRJ-005 | Campaign Project 5 | DS-CLN-006 | Branding | Muhammad Jawad | 2026-05-06 | 2026-05-20 | Briefing | 0% | OVERDUE
DS-PRJ-006 | Campaign Project 6 | DS-CLN-007 | Web Design | Sarah Khan | 2026-05-07 | 2026-05-21 | In Progress | 50% | OVERDUE
DS-PRJ-007 | Campaign Project 7 | DS-CLN-008 | UI/UX | Zain Ahmed | 2026-05-08 | 2026-05-22 | Review | 50% | OVERDUE
DS-PRJ-008 | Campaign Project 8 | DS-CLN-009 | Social Media | Amna Javed | 2026-05-09 | 2026-05-23 | Approved | 100% | Completed
DS-PRJ-009 | Campaign Project 9 | DS-CLN-010 | Packaging | Muhammad Jawad | 2026-05-10 | 2026-05-24 | On Hold | 50% | OVERDUE
DS-PRJ-010 | Campaign Project 10 | DS-CLN-001 | Branding | Sarah Khan | 2026-05-11 | 2026-05-25 | Briefing | 0% | OVERDUE
DS-PRJ-011 | Campaign Project 11 | DS-CLN-002 | Web Design | Zain Ahmed | 2026-05-12 | 2026-05-26 | In Progress | 50% | OVERDUE
DS-PRJ-012 | Campaign Project 12 | DS-CLN-003 | UI/UX | Amna Javed | 2026-05-13 | 2026-05-27 | Review | 50% | OVERDUE
DS-PRJ-013 | Campaign Project 13 | DS-CLN-004 | Social Media | Muhammad Jawad | 2026-05-14 | 2026-05-28 | Approved | 100% | Completed
DS-PRJ-014 | Campaign Project 14 | DS-CLN-005 | Packaging | Sarah Khan | 2026-05-15 | 2026-05-29 | On Hold | 50% | OVERDUE
DS-PRJ-015 | Campaign Project 15 | DS-CLN-006 | Branding | Zain Ahmed | 2026-05-16 | 2026-05-30 | Briefing | 0% | OVERDUE
DS-PRJ-016 | Campaign Project 16 | DS-CLN-007 | Web Design | Amna Javed | 2026-05-17 | 2026-05-31 | In Progress | 50% | OVERDUE
DS-PRJ-017 | Campaign Project 17 | DS-CLN-008 | UI/UX | Muhammad Jawad | 2026-05-18 | 2026-06-01 | Review | 50% | OVERDUE
DS-PRJ-018 | Campaign Project 18 | DS-CLN-009 | Social Media | Sarah Khan | 2026-05-19 | 2026-06-02 | Approved | 100% | Completed
DS-PRJ-019 | Campaign Project 19 | DS-CLN-010 | Packaging | Zain Ahmed | 2026-05-20 | 2026-06-03 | On Hold | 50% | OVERDUE
DS-PRJ-020 | Campaign Project 20 | DS-CLN-001 | Branding | Amna Javed | 2026-05-21 | 2026-06-04 | Briefing | 0% | OVERDUE
DS-PRJ-021 | Campaign Project 21 | DS-CLN-002 | Web Design | Muhammad Jawad | 2026-05-22 | 2026-06-05 | In Progress | 50% | OVERDUE
DS-PRJ-022 | Campaign Project 22 | DS-CLN-003 | UI/UX | Sarah Khan | 2026-05-23 | 2026-06-06 | Review | 50% | OVERDUE
DS-PRJ-023 | Campaign Project 23 | DS-CLN-004 | Social Media | Zain Ahmed | 2026-05-24 | 2026-06-07 | Approved | 100% | Completed
DS-PRJ-024 | Campaign Project 24 | DS-CLN-005 | Packaging | Amna Javed | 2026-05-25 | 2026-06-08 | On Hold | 50% | OVERDUE
DS-PRJ-025 | Campaign Project 25 | DS-CLN-006 | Branding | Muhammad Jawad | 2026-05-26 | 2026-06-09 | Briefing | 0% | OVERDUE
DS-PRJ-026 | Campaign Project 26 | DS-CLN-007 | Web Design | Sarah Khan | 2026-05-27 | 2026-06-10 | In Progress | 50% | OVERDUE
DS-PRJ-027 | Campaign Project 27 | DS-CLN-008 | UI/UX | Zain Ahmed | 2026-05-28 | 2026-06-11 | Review | 50% | OVERDUE
DS-PRJ-028 | Campaign Project 28 | DS-CLN-009 | Social Media | Amna Javed | 2026-05-29 | 2026-06-12 | Approved | 100% | Completed
DS-PRJ-029 | Campaign Project 29 | DS-CLN-010 | Packaging | Muhammad Jawad | 2026-05-30 | 2026-06-13 | On Hold | 50% | OVERDUE
DS-PRJ-030 | Campaign Project 30 | DS-CLN-001 | Branding | Sarah Khan | 2026-05-31 | 2026-06-14 | Briefing | 0% | OVERDUE
DS-PRJ-031 | Campaign Project 31 | DS-CLN-002 | Web Design | Zain Ahmed | 2026-06-01 | 2026-06-15 | In Progress | 50% | On Track
DS-PRJ-032 | Campaign Project 32 | DS-CLN-003 | UI/UX | Amna Javed | 2026-06-02 | 2026-06-16 | Review | 50% | On Track
DS-PRJ-033 | Campaign Project 33 | DS-CLN-004 | Social Media | Muhammad Jawad | 2026-06-03 | 2026-06-17 | Approved | 100% | Completed
DS-PRJ-034 | Campaign Project 34 | DS-CLN-005 | Packaging | Sarah Khan | 2026-06-04 | 2026-06-18 | On Hold | 50% | On Track
DS-PRJ-035 | Campaign Project 35 | DS-CLN-006 | Branding | Zain Ahmed | 2026-06-05 | 2026-06-19 | Briefing | 0% | On Track
DS-PRJ-036 | Campaign Project 36 | DS-CLN-007 | Web Design | Amna Javed | 2026-06-06 | 2026-06-20 | In Progress | 50% | On Track
DS-PRJ-037 | Campaign Project 37 | DS-CLN-008 | UI/UX | Muhammad Jawad | 2026-06-07 | 2026-06-21 | Review | 50% | On Track
DS-PRJ-038 | Campaign Project 38 | DS-CLN-009 | Social Media | Sarah Khan | 2026-06-08 | 2026-06-22 | Approved | 100% | Completed
DS-PRJ-039 | Campaign Project 39 | DS-CLN-010 | Packaging | Zain Ahmed | 2026-06-09 | 2026-06-23 | On Hold | 50% | On Track
DS-PRJ-040 | Campaign Project 40 | DS-CLN-001 | Branding | Amna Javed | 2026-06-10 | 2026-06-24 | Briefing | 0% | On Track
DS-PRJ-041 | Campaign Project 41 | DS-CLN-002 | Web Design | Muhammad Jawad | 2026-06-11 | 2026-06-25 | In Progress | 50% | On Track
DS-PRJ-042 | Campaign Project 42 | DS-CLN-003 | UI/UX | Sarah Khan | 2026-06-12 | 2026-06-26 | Review | 50% | On Track
DS-PRJ-043 | Campaign Project 43 | DS-CLN-004 | Social Media | Zain Ahmed | 2026-06-13 | 2026-06-27 | Approved | 100% | Completed
DS-PRJ-044 | Campaign Project 44 | DS-CLN-005 | Packaging | Amna Javed | 2026-06-14 | 2026-06-28 | On Hold | 50% | On Track
DS-PRJ-045 | Campaign Project 45 | DS-CLN-006 | Branding | Muhammad Jawad | 2026-06-15 | 2026-06-29 | Briefing | 0% | On Track
DS-PRJ-046 | Campaign Project 46 | DS-CLN-007 | Web Design | Sarah Khan | 2026-06-16 | 2026-06-30 | In Progress | 50% | On Track
DS-PRJ-047 | Campaign Project 47 | DS-CLN-008 | UI/UX | Zain Ahmed | 2026-06-17 | 2026-07-01 | Review | 50% | On Track
DS-PRJ-048 | Campaign Project 48 | DS-CLN-009 | Social Media | Amna Javed | 2026-06-18 | 2026-07-02 | Approved | 100% | Completed
DS-PRJ-049 | Campaign Project 49 | DS-CLN-010 | Packaging | Muhammad Jawad | 2026-06-19 | 2026-07-03 | On Hold | 50% | On Track
DS-PRJ-050 | Campaign Project 50 | DS-CLN-001 | Branding | Sarah Khan | 2026-06-20 | 2026-07-04 | Briefing | 0% | On Track
Formulas:
Overdue Status = IF([Status]="Approved", "Completed", IF([Due Date]<TODAY(), "OVERDUE", "On Track"))

## Team Allocation
Designer Name | Role | Active Projects | Weekly Capacity (Hrs) | Allocated Hrs | Utilization Rate (%)
Amna Javed | Senior Designer | 9 | 40 | 10 | 25%
Muhammad Jawad | UI/UX Specialist | 11 | 40 | 20 | 50%
Sarah Khan | Illustrator | 11 | 40 | 30 | 75%
Zain Ahmed | Junior Designer | 9 | 40 | 40 | 100%

## Financial Tracking
Project ID | Project Budget | Amount Invoiced | Amount Paid | Outstanding Balance | Invoice Status
DS-PRJ-001 | 1600 | 1600 | 800 | 800 | Partially Paid
DS-PRJ-002 | 1700 | 1700 | 850 | 850 | Partially Paid
DS-PRJ-003 | 1800 | 1800 | 1800 | 0 | Paid
DS-PRJ-004 | 1900 | 1900 | 950 | 950 | Partially Paid
DS-PRJ-005 | 2000 | 2000 | 0 | 2000 | Unsent
DS-PRJ-006 | 2100 | 2100 | 2100 | 0 | Paid
DS-PRJ-007 | 2200 | 2200 | 1100 | 1100 | Partially Paid
DS-PRJ-008 | 2300 | 2300 | 1150 | 1150 | Partially Paid
DS-PRJ-009 | 2400 | 2400 | 2400 | 0 | Paid
DS-PRJ-010 | 2500 | 2500 | 0 | 2500 | Unsent
DS-PRJ-011 | 2600 | 2600 | 1300 | 1300 | Partially Paid
DS-PRJ-012 | 2700 | 2700 | 2700 | 0 | Paid
DS-PRJ-013 | 2800 | 2800 | 1400 | 1400 | Partially Paid
DS-PRJ-014 | 2900 | 2900 | 1450 | 1450 | Partially Paid
DS-PRJ-015 | 3000 | 3000 | 3000 | 0 | Paid
DS-PRJ-016 | 3100 | 3100 | 1550 | 1550 | Partially Paid
DS-PRJ-017 | 3200 | 3200 | 1600 | 1600 | Partially Paid
DS-PRJ-018 | 3300 | 3300 | 3300 | 0 | Paid
DS-PRJ-019 | 3400 | 3400 | 1700 | 1700 | Partially Paid
DS-PRJ-020 | 3500 | 3500 | 0 | 3500 | Unsent
DS-PRJ-021 | 3600 | 3600 | 3600 | 0 | Paid
DS-PRJ-022 | 3700 | 3700 | 1850 | 1850 | Partially Paid
DS-PRJ-023 | 3800 | 3800 | 1900 | 1900 | Partially Paid
DS-PRJ-024 | 3900 | 3900 | 3900 | 0 | Paid
DS-PRJ-025 | 4000 | 4000 | 0 | 4000 | Unsent
DS-PRJ-026 | 4100 | 4100 | 2050 | 2050 | Partially Paid
DS-PRJ-027 | 4200 | 4200 | 4200 | 0 | Paid
DS-PRJ-028 | 4300 | 4300 | 2150 | 2150 | Partially Paid
DS-PRJ-029 | 4400 | 4400 | 2200 | 2200 | Partially Paid
DS-PRJ-030 | 4500 | 4500 | 4500 | 0 | Paid
DS-PRJ-031 | 4600 | 4600 | 2300 | 2300 | Partially Paid
DS-PRJ-032 | 4700 | 4700 | 2350 | 2350 | Partially Paid
DS-PRJ-033 | 4800 | 4800 | 4800 | 0 | Paid
DS-PRJ-034 | 4900 | 4900 | 2450 | 2450 | Partially Paid
DS-PRJ-035 | 5000 | 5000 | 0 | 5000 | Unsent
DS-PRJ-036 | 5100 | 5100 | 5100 | 0 | Paid
DS-PRJ-037 | 5200 | 5200 | 2600 | 2600 | Partially Paid
DS-PRJ-038 | 5300 | 5300 | 2650 | 2650 | Partially Paid
DS-PRJ-039 | 5400 | 5400 | 5400 | 0 | Paid
DS-PRJ-040 | 5500 | 5500 | 0 | 5500 | Unsent
DS-PRJ-041 | 5600 | 5600 | 2800 | 2800 | Partially Paid
DS-PRJ-042 | 5700 | 5700 | 5700 | 0 | Paid
DS-PRJ-043 | 5800 | 5800 | 2900 | 2900 | Partially Paid
DS-PRJ-044 | 5900 | 5900 | 2950 | 2950 | Partially Paid
DS-PRJ-045 | 6000 | 6000 | 6000 | 0 | Paid
DS-PRJ-046 | 6100 | 6100 | 3050 | 3050 | Partially Paid
DS-PRJ-047 | 6200 | 6200 | 3100 | 3100 | Partially Paid
DS-PRJ-048 | 6300 | 6300 | 6300 | 0 | Paid
DS-PRJ-049 | 6400 | 6400 | 3200 | 3200 | Partially Paid
DS-PRJ-050 | 6500 | 6500 | 0 | 6500 | Unsent
Total | 202500 | 202500 | 119150 | 83350